## Risk Register
Risk Register — TalkTalk 2015 Data Breach
Risk ID | Risk Title | Risk Description | Threat | Likelihood | Consequence | Risk Rating | Existing Controls / Mitigation | Risk Owner | Status | Date Identified
TT-01 | SQL Injection on Unpatched Legacy Web Pages | Hackers used a technique called SQL injection to break into TalkTalk's customer database. They got in through old website pages left over from a company TalkTalk had bought years earlier. This let them access personal and financial details for over 156,000 customers. | An outside hacker using a well-known method for attacking websites | 8 - Very Likely | Extreme | Extreme | The old pages had no security checks in place. Fix: regularly update and patch software, add a firewall to protect web pages, check that data entered into forms is validated, and test the website often for weaknesses. | Head of Application Security | Closed | 05 Aug 2026
TT-02 | Earlier Attack Attempts Not Detected or Acted On | Two smaller break-in attempts happened in July and September 2015, using the same method. Nobody noticed, so the same weakness was used again in October to steal data. | Hackers testing the website for weaknesses before the real attack | 8 - Very Likely | Major | High | There was no proper system watching for suspicious activity. Fix: set up ongoing monitoring of the website, and create a clear process for reacting quickly when repeated attack attempts are spotted. | Head of Security Operations | Closed | 05 Aug 2026
TT-03 | Inherited Insecure Infrastructure from Prior Acquisition | TalkTalk didn't realise that old web pages from a company it bought years before were still live and connected to a customer database. | Risk left behind from an old company purchase that nobody was managing | 6 - Somewhat Likely | Extreme | High | These old systems were never properly checked or listed. Fix: check the security of all systems whenever a company is bought, set deadlines to shut down or replace old systems, and regularly scan for forgotten systems. | Director of IT Integration / CISO | Closed | 05 Aug 2026
TT-04 | Incomplete Customer Breach Notification | A BBC investigation later found that about 4,500 affected customers were never told their data had been stolen, even though TalkTalk said everyone had been contacted. | An internal mistake in how the company handled telling customers after the breach | 6 - Somewhat Likely | Major | High | TalkTalk contacted customers but didn't properly check the list. Fix: build a clear process that confirms every affected customer was actually told, with a way to check nobody was missed. | Data Protection Officer | Closed | 05 Aug 2026
TT-05 | Extortion Threat Following Data Theft | Soon after the breach, someone claiming to be behind the attack contacted TalkTalk asking for money, and threatened to release or misuse the stolen data. | Criminals using stolen data to demand money from the company | 6 - Somewhat Likely | Major | High | There was no clear plan for dealing with this kind of threat. Fix: store less sensitive data, encrypt what is stored, and prepare a tested plan for how to respond if this happens again. | Executive / Crisis Management Team | Closed | 05 Aug 2026
TT-06 | Insufficient Protection of Stored Payment Card Data | Partial credit and debit card details for about 28,000 customers were exposed. The data was partly hidden but not properly encrypted. | Financial data being exposed during the wider data breach | 6 - Somewhat Likely | Major | High | The card data was masked but not encrypted, which is a weaker form of protection. Fix: encrypt sensitive financial data properly, follow payment industry security standards (PCI-DSS), and avoid storing full card details when not needed. | Data Protection Officer | Closed | 05 Aug 2026

## Legend & Scoring
Scoring Guide
Likelihood | Consequence | Risk Rating
1 - Rare | 1 - Insignificant | Low — Keep an eye on it.
2 - Very unlikely | 2 - Minor | Medium — Plan a fix.
3 - Unlikely | 3 - Moderate | High — Fix it soon and keep managers informed.
4 - Slightly unlikely | 4 - Major | Extreme — Fix it now and tell senior leaders straight away.
5 - Possible | 5 - Extreme
6 - Somewhat likely
7 - Likely
8 - Very likely
9 - Highly likely
10 - Almost certain